## Gantt Chart
GANTT CHART TEMPLATE | [6 empty] | Smartsheet Tip ➜ | [5 empty] | A Gantt chart's visual timeline allows you to see details about each task as well as project dependencies.
PROJECT TITLE |  | CAN bus Vulnerability Assessment |  |  |  |  | TEAM NAME | [6 empty] | Team CAN Bus
PROJECT MANAGER |  | Pooja Patil |  |  |  |  | DATE | [6 empty] | 2024-09-10
WBS NUMBER | TASK TITLE |  | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project overview plan
1.1 | Project requirements |  | 2024-09-10 | 2024-09-25 | 15 | 100% | bar: WEEK 1 M to WEEK 3 W
1.1.1 | Project overview plan |  | 2024-09-10 | 2024-10-03 | 23 | 100% | bar: WEEK 1 M to WEEK 4 F
1.2 | Research |  | 2024-09-10 | 2024-10-09 | 29 | 70% | bar: WEEK 1 M to WEEK 4 R
1.3 | Plan |  | 2024-09-10 | 2024-10-11 | 31 | 50% | bar: WEEK 1 M to WEEK 5 F
1.4 | Approval |  | 2024-10-25 | 2024-11-01 | 6 | 0%
1.5 | Begin initial setup |  | 2024-11-01 | 2024-11-07 | 6 | 0%
2 | CAN Interface Setup
2.1 | Device connectivity tested |  | 2024-11-01 | 2024-11-08 | 4 | 0% | bar: WEEK 4 M to WEEK 4 R
2.2 | Prepare for attack simulation |  | 2024-11-08 | 2024-11-14 | 3 | 0% | bar: WEEK 4 F; WEEK 5 T to WEEK 5 F
2.3 | Comfirmation |  | 2024-11-14 | 2024-11-17 | 3 | 0%
2.4 | Begin testing |  | 2024-11-17 | 2024-11-25 | 8 | 0%
3 | Attack Simulation/Mitigation
3.1 | Reconaissance |  | 2024-11-25 | 2024-11-29 | 4 | 0%
3.2 | Attack Simulation |  | 2024-11-25 | 2024-11-29 | 4 | 0%
3.2.1 | Traffic monitoring |  | 2024-11-25 | 2024-11-29 | 4 | 0%
3.2.2 | Document findings |  | 2024-11-29 | 2024-12-05 | 7 | 0%
3.3 | Mitigation plan |  | 2024-11-29 | 2024-12-05 | 7 | 0%
3.3.1 | Mitigation testing |  | 2024-11-29 | 2024-12-05 | 7 | 0%
3.3.2 | Mitigation validated |  | 2024-11-29 | 2024-12-05 | 7 | 0%
3.4 | Update charts/ Create Threat model |  | 2024-11-29 | 2024-12-05 | 7 | 0%
4 | Project Performance / Monitoring
4.1 | Project Objectives |  | 2024-09-25 | 2024-12-05 | 71 | 0%
4.2 | Quality Deliverables |  | 2024-11-13 | 2024-12-05 | 22 | 0%
4.3 | Effort and Cost Tracking |  | 2024-10-10 | 2024-12-05 | 56 | 0%
4.4 | Project Performance |  | 2024-11-25 | 2024-12-05 | 11 | 0%